## Sheet1
Daywise Status of group members
| Rajeshwari Bhirud | Prakash Devar | Shankar Linganwad | Hutesh Mahajan | Shubham Sethi
Dates
2020-10-27 | Designing of class diagram | test case documetation | Designing of class diagram | Designing of class diagram | Designing of class diagram
2020-10-28 | working on add amount microservice | working on fund transfer and show transaction microservice | learning and implemeting swagger feign ad ribbon client (for proxy implementation) implementing same for creating wallet account microservice | learning and implemeting swagger feign ad ribbon client (for proxy implementation) implementing same for user login microservice | learning and implemeting swagger feign ad ribbon client (for proxy implementation) implemeting same for showig balance in wallet microservice
2020-10-29 | Implementing wallet database provider,implementing of eureka server,swagger2,and working on eception handling and validations | implmeting fund transfer and show transaction microservices | implementing login database provider for wallet creation | implementing login database provider for user login adding user implmenting swagger and working on exceptio handling and validation | implemeting of wallet account microservice
| Hutesh mahajan | user login
| shankar | add user
| rajeshwari | add amount
| shubham | show balance
| prakash | traner fund and show transaction